## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
DOCUMENT NAME: | TEST PLAN
CREATED ON: | DD-MMM-YYYY
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | Linkedin-Replica
PROJECT ID
INTERN NAME | Utekar Pranit Ganesh
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
Functional Testing: Ensures that all features and functionalities work as expected, covering aspects like user registration, profile creation and job posting. Usability Testing: Focuses on user experience and interface design, ensuring that the platform is user-friendly and accessible. Performance Testing: Evaluates the platform's speed, scalability, and responsiveness under various load conditions to ensure it can handle traffic effectively. Security Testing: Identifies vulnerabilities and ensures the platform's protection against data breaches, phishing attacks, and other security threats. Compatibility Testing: Ensures the platform works correctly on various devices, browsers, and operating systems, optimizing the user experience across different platforms. Regression Testing: Verifies that new features and updates do not negatively impact existing functionalities.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
User Registration and Authentication: User registration process, including account creation and verification. User authentication, login User Profiles: Profile creation, editing, and deletion. Profile visibility settings and privacy controls. User profile information, including name, headline, summary, contact details, education, work experience, skills, and endorsements. Content Creation and Sharing: Posting text updates, articles, images, and videos. Privacy and Security: Privacy settings and controls for user profiles and content. Security measures to protect user data and prevent unauthorized access.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Customization for Specific Clients: Customization and configuration of the platform for specific client requirements that go beyond the standard LinkedIn replica are out of scope. Offline Functionality: Testing of offline functionality or features that require the platform to work without an internet connection is not part of this scope
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
The overall objective of testing in the LinkedIn replica project is to verify that the software meets quality standards, is free from critical defects, and provides a reliable, user-friendly experience for platform users. This includes ensuring that the platform's features, functionalities, and non-functional aspects operate as intended and meet user expectations. Testing aims to identify and mitigate issues and risks, ultimately contributing to the successful launch and ongoing maintenance of the platform.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
Developer Tester
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
The test methodology selected for the project is Agile Testing, Iterative Development: Agile testing aligns with the project's iterative development approach, where features are developed incrementally in sprints. This methodology allows for continuous testing throughout the development lifecycle, promoting early defect detection and rapid feedback. Flexibility and Adaptability: Agile testing is well-suited to projects with evolving requirements and priorities. In the dynamic landscape of a social networking platform, requirements may change, and new features may be introduced based on user feedback and market trends. Agile allows the testing process to adapt to these changes efficiently. Customer-Centric Focus: The LinkedIn replica project places a strong emphasis on user satisfaction and feedback. Agile methodologies, particularly Scrum, emphasize collaboration with stakeholders, including end-users, to gather and prioritize requirements. Testing aligns with this focus on user needs and expectations
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
1. Unit Testing: Objective: To test individual components, functions, or modules in isolation to verify their correctness. Scope: Developers conduct unit testing to ensure that code units meet their design and functional specifications. Tools: Testing frameworks like Jest, JUnit, or NUnit may be used for unit testing. 2. Integration Testing: Objective: To verify the interactions and interfaces between different modules, components, or services within the application. Scope: Identify and rectify issues arising from the integration of different system components. Tools: Postman, JUnit, and custom scripts for API testing. 3. Functional Testing: Objective: To validate that the application functions according to the defined requirements and specifications. Scope: Test the core functionality, user interactions, and key features of the LinkedIn replica. Tools: Test management tools (e.g., TestRail), Selenium for web application testing, Appium for mobile app testing.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
1. Bug Resolution: Fix: Bugs that directly impact critical functionalities, security, or user experience are assigned a status of "To Be Fixed" and are scheduled for resolution in the upcoming development sprints. Postpone: Some bugs may be deemed non-critical or may require further investigation. These are marked as "Postpone" and are revisited later based on available resources and project priorities. Duplicate: Duplicate bug reports are identified, and only one instance of the bug is kept for resolution. The others are marked as duplicates and linked to the original report. Won't Fix: In some cases, a bug may be considered too minor to warrant immediate attention or may be a result of a design choice. Such bugs are marked as "Won't Fix" and documented for reference. 2. Bug Prioritization: Bugs are prioritized based on several factors to determine their importance and urgency for resolution: Severity: Bugs are categorized by their severity, such as Critical, Major, Minor, or Trivial, based on their impact on the system and users. Priority: Bugs are assigned a priority level, considering factors like business impact, user impact, and strategic importance. User Feedback: Bugs reported by users or customers may be given higher priority, especially if they significantly affect user experience. Regulatory Compliance: Bugs related to legal or compliance requirements are often given high priority. Functional Impact: Bugs affecting core functionality are generally higher in priority than those related to non-essential features. 3. Bug Scheduling: Based on the priority and severity of the bugs, a schedule for their resolution is determined:
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Test Coverage: A predefined percentage of test coverage, based on requirements, user stories, and risk analysis, is achieved. This includes functional, non-functional, and edge case coverage. Critical Bug Resolution: All critical and high-priority bugs have been identified, resolved, and verified as fixed. Acceptance Criteria: All user stories and project requirements, including acceptance criteria, have been tested and met. Usability and Accessibility: Usability testing has been conducted, and the application's user interface is user-friendly and intuitive. Accessibility testing has been performed, and the application complies with accessibility standards
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
1. Test Planning Phase: Test Plan: A comprehensive document outlining the testing strategy, objectives, scope, schedule, resources, and risk assessment. Test Strategy: A high-level document describing the overall approach, methodologies, and tools to be used for testing. Test Schedule: A timeline or Gantt chart illustrating the testing activities and milestones. Test Environment Setup Plan: Documentation detailing the configuration and setup of the test environments. 2. Test Design Phase: Test Cases: Detailed documents specifying individual test cases, including test inputs, expected outcomes, and step-by-step execution instructions. Test Data: Requirements for test data and datasets necessary for executing test cases. Test Scripts: Automated test scripts for automated testing efforts, if applicable. Test Scenarios: High-level descriptions of test scenarios that encompass multiple test cases.
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Usability and Accessibility Testing Tools Code Review and Static Analysis Tools
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Processor: Dual-core or Quad-core processor (e.g., Intel Core i3 or equivalent) RAM: 8 GB Storage: 256 GB SSD Network: Stable internet connection Graphics: Standard integrated graphics card Operating System: Windows 10/11, macOS, or Linux Development Environment: Modern IDEs
ADDITIONAL COMMENTS
none as such
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
posts | Used testing tools for user behavior analysis. | 2023-09-21 | 2023-09-24 | Developer | PASSED | no issues found
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.